Evaluation Report

of the

Whānau Ora Health Impact Assessment

on the

Draft Wairarapa Alcohol Strategy

Quigley and Watts Ltd

June 2010

Contact:

Celia Murphy

Quigley and Watts Ltd

PO Box 24266

Wellington 6142

(04) 3842049

021 2327519

celia@quigleyandwatts.co.nz

Groups referred to in the document

WOHIA Team

Lucy Cotterill - Health Promoter Wairarapa DHB

John Tibble - Māori Cultural Advisor Wairarapa DHB

Rob Quigley - Quigley and Watts Ltd

Kate Marsh - Quigley and Watts Ltd

HIA Consultant

Rob Quigley - Quigley and Watts Ltd

WOHIA Team Leader

Lucy Cotterill - Health Promoter Wairarapa DHB

Glossary of Abbreviations & Acronyms

CAAG 	 	Community Alcohol Action Group

DHB		District Health Board

HIA 		Health Impact Assessment

LTCCP 		Long Term Council Community Plan

WOHIA	 	Whānau Ora Health Impact Assessment

Contents

1 Introduction	4

1.1 Objectives/aims of the WOHIA	5

1.2 Screening and Scoping	6

1.2.1 Focus of the WOHIA	6

1.2.2 Populations affected	7

1.3 Evaluation objectives	8

1.4 Limitations of the evaluation	8

1.5 Data collection methods	9

1.6 Data analysis	9

2 Process Evaluation	10

2.1 Evaluation of the Screening/Scoping meeting	10

2.2 Evaluation of the Appraisal phase	10

2.3 Evaluation of the literature review	13

2.4 Evaluation interviews	14

2.4.1 Were the aims of the WOHIA achieved?	14

2.4.2 Strengths of the WOHIA	16

2.4.3 Constraints of the WOHIA process	17

2.4.4 How could the process have been improved	18

2.4.5 Effective use of resources	19

2.5 The report	19

3 Outcome Evaluation	20

3.1 The short-term outcome – the impact of the HIA	20

3.2 WOHIA buy-in	23

4 Discussion and Conclusions	24

4.1 The short term impact of the WOHIA	24

4.2 Did the WOHIA meet its objectives?	24

4.3 The strengths and constraints of the WOHIA process	25

4.4 Other evaluation objectives and positive outcomes	26

4.5 Conclusions	26

Appendix 1: Schedule for key informant interviews	27

Questions for direct participants	27

Questions for community stakeholders	30

Appendix 2: Evaluation forms given to participants	32

Screening/Scoping workshop	32

Appraisal workshop	33

- 1 	Introduction

The draft Wairarapa Alcohol Strategy (draft Strategy) was written in response to community concern about alcohol related harm in the Wairarapa Region. An initial review of the regional situation carried out by the Masterton District Council indicated the most effective way of addressing multiple, interrelated issues would be under the umbrella of a comprehensive alcohol strategy.

Several key stakeholders in the region work together on community based projects and needs identification through community network groups. One of these is the Community Alcohol Action Group (CAAG), which consists of 15 governmental and non-governmental Wairarapa based organisations. The draft Strategy was developed by this community group and was put forward for adoption by the three District Councils in the Wairarapa region; Masterton, Carterton and South Wairarapa District Councils.

The Wairarapa DHB was granted funding from the Ministry of Health HIA Support Unit Learning by Doing Fund late in 2009 to carry out a Whānau Ora Health Impact Assessment (WOHIA) on the draft Wairarapa Alcohol Strategy.

The Health Impact Assessment (HIA) was led by a Health Promoter and Māori Cultural Advisor both from the Wairarapa DHB assisted by HIA consultant Robert Quigley (and his colleagues) of Wellington-based Quigley and Watts Ltd. The HIA consultant’s services – facilitation, mentoring and a brief review of the literature, were funded by the Ministry of Health, HIA Support Unit’s Learning by Doing fund, as was this evaluation. The evaluation was also completed by Quigley and Watts Ltd.

The WOHIA was conducted to answer the following questions:

- How will the implementation of the draft Strategy affect the health and wellbeing of the local Māori population?

- Are there any recommendations to the draft Strategy that would improve health and wellbeing or reduce harmful impacts on health and wellbeing?

The methods used in this WOHIA were:

- initial discussions around the WOHIA process and to determine if a WOHIA should occur

- a Screening/Scoping meeting to plan the boundaries and approach of the WOHIA with key informants

- a summary of selected literature

- development of a profile of the Wairarapa community

- appraisal workshop with key stakeholders

- reports to participants and decision makers.

The timeframe for the WOHIA was constrained. Public submissions closed on the draft Strategy on 29th January 2010. Wairarapa DHB asked for dispensation from the Council to undertake the WOHIA outside the public submission timeframe and dispensation was granted. It was made clear that the WOHIA would not affect the submission hearing date set down for 10 March, and so the WOHIA had to be completed by 3 March 2010 to inform the policy makers. On 26 February (after the first draft of the report had been written) the hearing date was moved by Council to the later date of 7 April with the report having to reach Council no later than 5pm on 26 March. The WOHIA kept to the original timeframes outlined in the planning workshop, and the draft report was sent to stakeholders for review on 26 February 2010 as planned.

This report presents the process evaluation results of the WOHIA and the short term impacts of the WOHIA.

## 1.1	Objectives/aims of the WOHIA

The WOHIA was conducted to answer the following questions:

- How will the implementation of the draft Strategy affect the health and wellbeing of the local Māori population?

- Are there any recommendations to the draft Strategy that would improve health and wellbeing or reduce harmful impacts on health and wellbeing?

The aims of the WOHIA were to:

- assess the links between alcohol strategies, partnership working and consistency of approach, alcohol related harm and health outcomes in NZ

- Identify existing alcohol related inequalities in Wairarapa health and wellbeing outcomes, in particular, for Māori and youth

- identity the potential positive and negative impacts of the draft Strategy on health and wellbeing

- identify current strengths within the community to undertake the draft Strategy,  as well as gaps, limitations and resource development needs, to ensure the draft Strategy is sustainable

- provide evidence-based recommendations to enhance the draft Strategy’s potential positive impacts on health and wellbeing and mitigate potential negative impacts

- provide some guidelines and recommendations to key stakeholder groups on how to support, implement and develop the draft Strategy within their organisations and in partnership with other agencies and organisations.

## 1.2	Screening and Scoping

Due to time limitations the Screening and Scoping stages of the WOHIA of the draft Strategy were carried out at the same time.  The meeting took place at the Wairarapa DHB on 12 February to determine if a WOHIA should occur and to scope the boundaries and approach of the WOHIA.

Fourteen stakeholders from a range of organisations which included health providers, the Ministry of Social Development, the three local Councils, Police, Iwi and a re from the a Pacific Community Group were invited to the meeting. Twelve people attended the meeting; this number included the two people from the DHB who were leading the WOHIA and the facilitator from Quigley and Watts Ltd. Two of those who attended the meeting belonged to CAAG. Those who attended represented all of the sectors invited except local Iwi.

Participants were introduced to the WOHIA process in meetings held prior to this meeting and after a brief recap of the WOHIA process went on to discuss and decide on the scope and process the WOHIA should follow.

- 1.2.1 	Focus of the WOHIA

Participants at the Screening/Scoping meeting agreed the primary determinant of health the WOHIA would focus on was increased partnership working – to assess how the proposed actions in the strategy would be enhanced through this.

This was decided as participants identified increased partnership and consistency between organisations as the two most substantial changes to the draft Strategy from alcohol related activities already in place in the Wairarapa. The HIA consultant believed this was a substantial finding from the HIA approach, as up to this point it was unclear which parts of the draft Strategy were new initiatives and which parts were just a continuation of existing activities. Participants expressed some surprise that increased partnerships and consistency of approach between agencies was the only new approach suggested in the draft Strategy. Careful reading of the draft Strategy showed that all the activities listed in the draft Strategy were already existing work programmes.

The meeting also agreed there would also be consideration of the likely impacts of increased consistency across organisations in relation to the proposed actions of the draft Strategy.

- 1.2.2	Populations affected

The scoping group decided on the populations groups for the WOHIA. It was decided that the WOHIA should focus primarily on communities, encompassing both organisations and whānau. Justification for these populations was determined by the focus of the WOHIA, as increased partnership could not be assessed without looking at the impact on organisations and in turn Whānau.

Participants agreed the central question for the Whānau Ora HIA was:

How could increased partnership and consistency between organisations impact positively or negatively on the health and  wellbeing of Māori in the Wairarapa with a special focus on whānau?

There was some discussion about holding Appraisal Workshops in the community at local marae and consulting with Pacific people and youth but it was decided that kind of consultation would be more appropriate at the implementation stage of the Alcohol Strategy. The tight timeframe of the WOHIA would also have made it difficult to arrange community consultation workshops. One of the key informant interviewees noted that, even though the community consultation was not undertaken as part of the WOHIA, representatives from the communities were invited to participate in the Appraisal Workshop.

The meeting decided one Appraisal Workshop would be held and participants suggested possible organisations who should be invited.

It was also agreed that a community profile would be written using existing information from local and national sources to provide background information which would be presented at the Appraisal Workshop and included in the WOHIA Report.

It was also decided that a brief literature review would be carried out.

## 1.3	Evaluation objectives

The evaluation of the WOHIA had the following objectives:

1.   To provide information to assist in improving the HIA process for future HIA work.

2.   To determine, in terms of process:

- if the objectives of the WOHIA were met

- the strengths of the WOHIA process

- the constraints of the WOHIA process

- possible ways the WOHIA process could have been improved

- whether the resources used throughout the WOHIA process were used  effectively.

3. To determine, in terms of impact:

- the impact of the WOHIA on the Wairarapa Alcohol Strategy

- if the WOHIA added value to the planning process? If so in what ways?

- if the recommendations were / weren’t taken on board, why / why not, and the consequences .

4. With regard to overall issues the evaluation aims to identify:

- key factors that achieved buy-in into the WOHIA process and outcomes, particularly at the senior management and political level

- key lessons from this WOHIA

5. With regard to short-term outcome evaluation:

- would the WOHIA encourage ongoing monitoring of health impacts by those whose policies or programmes are the subject of the WOHIA

- whether or not the recommendations were accepted by the three Councils.

## 1.4	Limitations of the evaluation

The very short time frame which was necessary to carry out the HIA process did not allow for formative evaluation to include feedback at key stages to assist the HIA team to reflect on their progress and make changes as the HIA proceeded. In addition only short term outcomes are able to be measured in the timeframe. Long term health outcomes for Māori are not able to be measured as a part of the evaluation of the WOHIA.

## 1.5	Data collection methods

Evaluation data was gathered by;

- listening to voice recordings of the Screening/Scoping Meeting and Appraisal Workshop

- analysis of the evaluation forms filled out by participants who attended the  Screening/Scoping Meeting and the Appraisal Workshop.

- document analysis of the:

  - report of the Screening/Scoping Meeting

  - WOHIA Final Report

- key informant interviews. Two interview schedules were developed for these interviews. One schedule listed the questions for discussion with those directly involved with developing and implementing the WOHIA process – the Wairarapa DHB team. The other schedule was for local community stakeholders who attended the meetings and workshops. In all five people were interviewed, two from the WOHIA team at the DHB and three community stakeholder participants. Two of the community participants chose to be interviewed together. The interviewees were agreed in discussion with the WOHIA team. The community stakeholders participants were selected because of their close involvement with the draft Strategy and because they were the only community stakeholders to attend both the Screening/Scoping Meeting and the Appraisal Workshop.  All the participants were interviewed by phone.

## 1.6	Data analysis

All data was analysed for key themes specific to the WOHIA evaluation objectives and other relevant issues raised by interviewees.

# 2	Process Evaluation

Section Two reports on evaluation objective two.

## 2.1	Evaluation of the Screening/Scoping meeting

Six of the twelve participants who attended the Screening/Scoping Workshop returned evaluation forms. All six either ‘strongly agreed’ or ‘agreed’ that:

- they understood why the WOHIA was to be undertaken

- why the WOHIA was on this topic

- they understood the focus of the WOHIA

- they were able to contribute to the decisions made at the meeting

- they were willing to continue to be involved

- they would consider using WOHIA for other projects that are/will be occurring

Two participants identified the main strengths of the session as being focussed and gave the opportunity for ‘shared talk to unpack what it all means for different people.’

Five people made suggestions they believed could have improved the scoping session. Four people suggested that they needed more background information on the WOHIA, the draft Strategy and CAAG before the meeting. Two felt more time was needed for discussion and that the allocated time was not long enough.

In other comments one participant indicated that some people did not seem to understand whānau ora and another noted that consulting whānau and the community would have been good had time been available to do so.

Although these evaluation forms were quite positive it is disappointing more people did not return the forms.

## 2.2	Evaluation of the Appraisal phase

It was decided that one Appraisal Workshop was to be held, due to time pressures. The meeting, held on 22 February, was attended by 20 people, four of these were the members of the WOHIA team and consultants, with the other 16 representing the local community. The attendees came from a wide range of organisations including the DHB, local PHO, Māori health providers, Council staff from the three areas included in the draft Strategy, Police, ALAC, Ministry of Social Development, ACC and some who were associated with the alcohol industry – the Hospitality Association of New Zealand and the local Licensing Trust. Nine of the attendees were members of CAAG which were responsible for initiating and drafting the Strategy.

Sixteen of the 20 participants who attended the Appraisal Workshop returned evaluation forms.

The evaluation forms generally indicated attendees found the workshop worthwhile with most participants either selecting the ‘Strongly agree’ and ‘Agree’ options on all of the questions on the evaluation form.

The majority of participants noted the strengths of the workshop were:

- the development of ‘relationships, new and renewed’

- that it allowed debate and discussion and time to ‘think through the solutions’

- the willingness ‘of community representatives to contribute’

- ‘the small group participation’

- and the ‘interactive’ way the meeting was run.

Seven of the participants said good facilitation of the workshop was one of its strengths, workshops were facilitated by Quigley and Watts Ltd. One noted that the facilitation kept the meeting ‘on track and focused’. Another identified ‘The skill of the facilitator to drive the process to reach conclusions’ as one of the strengths of the workshop.

Although one person disagreed with the statement ‘The participants had suggested ways the Strategy might affect the determinants of wellbeing for families’ and the statement ‘The workshop had been useful to develop and maintain links with people across the sector/s’ he/she listed that one of the main strengths of the workshop was ‘The ability to share and discuss various points’ .

Although one participant indicated he/she would not consider the HIA process for other projects he/’she identified the workshops was an ‘opportunity for discussion’.

The workshop divided into two small groups to discuss and identify:

- how increased partnership and consistency between stakeholder organisations impact on the wellbeing of whānau

- which of these impacts were the most important

- and, to develop recommendations which would improve partnership and consistency in the Alcohol Strategy and therefore its outcomes.

One of the community key informant participants and one of the evaluation questionnaires noted that the two groups provided very different feedback. The comments from one of the groups were much more focussed on the specific topic of partnership and consistency that the WOHIA was addressing. The other group provided more general comments relating to alcohol related harm, the draft Strategy itself and general solutions rather than those related to partnership and consistency.

Two factors seemed to contribute to this difference in the discussion – the make up of the two groups and a difference in how the two facilitators managed the groups. This was perceived to be both a strength and a weakness by different participants. Some saw it as diversity of discussion and a good thing and the whole point of bringing people together while a couple of others perceived it to be negative. Both groups were facilitated by staff from Q & W Ltd.

One of the key informant interviewees, despite being quite positive about the whole WOHIA process and the outcomes, described the Appraisal Workshop as ‘an exercise in frustration’. This was because the person perceived that not all could ‘see the difference between the Strategy and the HIA that they were supposed to be discussing’.

The development of the draft Strategy and the perceived lack of consultation associated with its development created a sticking point for several participants and a couple of people commented so in their evaluation forms. One of the key informant interviewees noted, the facilitator allowed these people to ‘have their say and then moved them [the discussion] on’.

One person perceived that ‘there was not the right mix of people’ at the workshops, however there were 20 people from a range of different organisations at the meetings. Over half of them belonged to CAAG, of which a few members were responsible for writing and producing the draft Strategy.

The strengths of the workshop described above, and the overwhelming positive feedback from the response forms meant that the material gathered at the Appraisal Workshop was ample to develop recommendations on how the draft Strategy might be improved.

## 2.3	Evaluation of the literature review

The short timeframes for the WOHIA resulted in little time for an in-depth literature review however, a summary of selected literature was completed. The authors described it as ‘a brief examination of relevant evidence for relationships between clear strategic direction; partnership, collaboration and consistency across sectors and organisations; and public health outcomes / whānau ora.’

The summary was carried out by Quigley and Watts Ltd. It was used for internal use only by Wairarapa Public Health and Quigley and Watts Ltd, to inform the WOHIA report and was not published or distributed with the final WOHIA report.

The literature used in the summary was sourced from key websites which included; Ministry of Social Development, Ministry of Health, State Services Commission Managing for Outcomes, Local Government New Zealand, Local Futures Project and a brief internet search using Google, Google Advanced and Google Scholar search engines.

The authors noted that due to the very limited search time the review was an extremely brief consideration of a small amount of literature and that it was not possible to draw conclusions. However it did raise a number of relevant points which identified that though there appeared to be little evidence that directly linked collaborative effort with health or social outcomes, there were gains such as improved relationships, partnerships and better strategic planning to be made by such efforts which would be likely to have beneficial effects.

Summary

The following points summarised the key information found in the literature review:

- Little evidence was located to directly link cross-sector collaboration with health or social outcomes; however there is information on expected gains and best practice principles.

- Examples of benefits of collaboration include better processes, improved relationships, a greater capacity to respond to local needs, and a more efficient use of resources. Leadership and a community-based approach seem to be key success factors for effective collaboration.

- There is a particular lack of evaluation of the impact of regional collaboration/partnership and service integration on Māori outcomes, and problems with government engagement with Māori.

- While there is a lack of hard evidence, greater cross-sectoral collaboration and integrated service delivery is increasingly seen by national, regional and local organisations as an essential way to address complex social problems and achieve better outcomes.

- Cross sectoral collaboration and partnerships are viewed as fundamental elements of successful strategic planning.

- Community strategic planning, which has an even stronger emphasis on collaboration and partnership to meet community needs, is increasingly used in New Zealand and internationally.

- Partnership may mean different things to different people, for instance a bicultural model for partnering is needed for the formation of relationships between Māori and non-Māori organisations at the local level.

- Community-based cross sectoral initiatives (at the service level) have been found to be effective in meeting health and social development objectives, and appear to work well for disadvantaged groups.

Though limited these findings suggested it was worth pursuing the collaboration theme of the WOHIA and the WOHIA team found the review useful in developing the recommendations to be included in the final report.

## 2.4	Evaluation interviews

As outlined earlier five key informants were interviewed as part of this process, different interview schedules were developed for the community and DHB stakeholders with the schedule for the DHB participants seeking more detail about the objectives of the WOHIA.

- 2.4.1	Were the aims of the WOHIA achieved?

Aim 1. Assess the links between alcohol strategies, partnership working and consistency of approach, and alcohol related harm and health outcomes in NZ

While the WOHIA team were able to find links between working in partnership and consistency of approach resulting in positive outcomes it was difficult to link these factors with reducing alcohol related harm and positive health outcomes in New Zealand. So, while it was possible to say a strategy which promotes collaborative and consistent approaches to alcohol related harm is likely to be beneficial, it was not possible to directly connect working in partnerships with positive health outcomes.

Aim 2. Identify existing alcohol related inequalities in Wairarapa health and wellbeing outcomes, in particular, for Māori and youth

The WOHIA team leader did not think this aim was achieved as very little local Wairarapa alcohol data, especially relating to Māori and youth, was found. The team was able to find national alcohol related data but local evidence was not of a very good quality and largely anecdotal from practitioners and clinicians working in the area. The team also felt that the local links between alcohol and inequalities were not clear. The discovery that little local data was available was the basis of the recommendation to develop a clear and comprehensive problem description of alcohol harm within the Wairarapa to set the context for the Strategy.

Aim 3. Identity the potential positive and negative impacts of the Draft Strategy on health and wellbeing

The WOHIA team believe this aim was achieved. There were five evidenced based recommendations based on the impacts of the draft Strategy identified during the WOHIA and included in the final report. These included clear recommendations around health and wellbeing which were established using the causal pathway process. The impacts were identified by participants during the Appraisal Workshop.

Aim 4. Identify current strengths within the community to undertake the draft Strategy, as well as gaps, limitations and resource development needs that will ensure the draft Strategy is sustainable

The WOHIA team commented that the 20 different local organisations which were consulted during the WOHIA, most which contributed to the WOHIA in some way, were the organisations which would be implementing the Strategy. The team felt the willingness of the organisations to participate in the WOHIA was a demonstration of their interest and commitment to the Strategy. However, because there was no implementation plan associated with the draft Strategy, and it did not identify roles and responsibilities, it was difficult to ascertain who would take ownership of particular roles or tasks. The recommendations in the WOHIA report identified the need for both the Strategy and the associated implementation plan to clearly state specific roles and responsibilities and, for existing and new resources that would be required to be identified.

Aim 5. Provide evidence-based recommendations to enhance the draft Strategy’s potential positive impacts on health and wellbeing and mitigate potential negative impacts

The final report of the WOHIA included five evidenced based recommendations which, if instigated and followed through in the redrafting of the Strategy and development of the implementation plan, should enhance the potential for positive impacts and mitigation of potential negative impacts. These impacts and the mechanisms to deal with them were identified by the community in the Appraisal Workshop and were supported by information from the literature review.

Aim 6. Provide some guidelines and recommendations to key stakeholder groups on how to support, implement and develop the draft Strategy within their organisations and in partnership with other agencies and organisations.

The overall recommendations made in the WOHIA report reflect the ways in which stakeholders can work together. The WOHIA team believed the process of working together on the WOHIA not only increased awareness of the Strategy itself among a wide range of stakeholders involved but also raised awareness of ways in which the community could work together to implement it. The team hope that when the Strategy is implemented the WOHIA will have made the community aware of the necessity to work together and that organisations will be looking for ways to help each other to achieve positives outcomes.

- 2.4.2	Strengths of the WOHIA

Both the WOHIA team and the community stakeholder key informants described the WOHIA as a very positive process. The strengths of the WOHIA process identified by the key informants included that :

- the process and desired outcomes were clear

- all stakeholders had the opportunity to discuss the issue in a structured way

- it is a good way of getting stakeholders involved

- there is an end date and an outcome (the report and recommendations) – ‘not just attending meetings and talking about it with nothing to show for it in the end’

- it got stakeholders together to discuss a common concern

- it included all sectors working in, and with concerns about, alcohol related harm, were invited to participate

- there was good consultation with Māori

- meetings were well attended

- helped to get community buy-in to the Strategy that would assist with implementation later

- it helped to build relationships in the community

- positive and negative impacts of the draft Strategy were well discussed

- the recommendations were evidenced based

- a large number of organisations were consulted during the process

- it got health on to the agenda of a number of organisations whose core work is not health.

The WOHIA team leader commented on the value of working with both the Māori Health team at the DHB and CAAG and noted that both had a ‘big influence on getting so many stakeholders involved.’ This person also indicated that the large number of stakeholders who participated in the WOHIA gave a strong message to the Councils that this is an important issue and that those who took part in the WOHIA wanted their views to be heard.

There was a difference of opinion expressed about the value of getting the ‘people on the ground, like the Police off the beat’ and the senior policy makers together. The Council employee saw value in getting these two groups talking together but several other participants thought the two groups should have been divided into two separate groups.

Two participants noted the key strength of the WOHIA was that it identified the shortcomings of the draft Strategy and made recommendations as to how it might be improved.

The facilitation of the meetings, more particularly the Appraisal Workshop, was noted by two of the community stakeholders as a strength. They believed the facilitation of this meeting prevented the process from being derailed by a couple of people who held strong views. The two participants who were interviewed together felt some of the people at the workshop ‘did not understand the process and were suspicious of it’ but that the facilitator had managed these people well.

The Council participant described the WOHIA as being ‘a bit like a peer review of the Strategy’ and as being a ‘very positive’ and ‘clear process’.

- 2.4.3	Constraints of the WOHIA process

All of the key informants identified the short timeframes in which the WOHIA had to be completed as the main constraint. A change of staff at the DHB late in 2009 and the Christmas break were noted as unavoidable reasons for the time pressure. Generally participants thought the process had gone as well as could be expected given the time limitations. However all noted that the short lead in time for the meetings meant that some stakeholders could not be present at all the meetings. This was certainly apparent when the lists of attendees of the Screening/Scoping Meeting and the Appraisal Workshop were compared. Apart from DHB and WOHIA team members only three people attended both meetings. However there was a broad scope of stakeholder organisations represented at both meetings.

The Council key informant noted that although the timeframe created pressure, it had the benefit of keeping the issue ‘on the top of the mind’. This participant felt the short time was preferable to a process where meetings were ‘dragged out’ over a long period as people lose focus between meetings and time is wasted going over the same ground when people meet infrequently.

The other two community stakeholders thought the WOHIA started too late in the draft Strategy development process and that as a result it was too rushed. Both thought they needed more time to go into the issues in more depth, that more time was needed for more discussion and for more people to be consulted. They noted that because people had not been consulted and involved in the development of the draft Strategy ‘they were offended and needed time to get over that’ before they could contribute to the WOHIA.

The WOHIA team leader felt more time would have allowed for more community consultation which would have increased awareness of the Strategy and make implementation of the Strategy easier.

- 2.4.4	How could the process have been improved

Two of the participants felt there were a number of people who did not understand the HIA process and could not separate the WOHIA from the draft Strategy and wasted time at the meetings by trying to ‘re-litigate’ the draft Strategy.

These two participants also suggested the fact that some of the attendees at the meetings did not understand the WOHIA process and could not separate the process of developing the draft Strategy from the WOHIA process was unhelpful. They recommended all participants be given a an ‘HIA 101’  document that explained clearly the purpose, what would be expected of them, that HIA was a supportive way of working in the community and that there would be ongoing benefits for them before coming to the  WOHIA meetings. They suggested a ‘pre-hui’ might be one approach to cover this information.

In fact the WOHIA team leader and her predecessor had spent time with a number of the organisations explaining WOHIA and the process late in 2009 before the Screening/Scoping Meeting and Appraisal Workshop began. A introduction to HIA workshop was held in late November for the benefit of involved organisations.

- 2.4.5	Effective use of resources

The two DHB participants noted approximately 10.5 weeks of a full time equivalent (FTE) was spent on the WOHIA over the period from December to the end of March when the bulk of the work was done. In addition to this the consultants spent the equivalent of 2.7 weeks of an FTE during the same period. The WOHIA team leader felt that, though it was a rush, the limited time meant the team had to be decisive and focussed which was positive. She also felt Quigley and Watts Ltd time had been used effectively.

The DHB Māori Cultural Advisor from the Māori Health Unit commented that his involvement was time well spent. He felt the assistance of the Māori Health team helped ensure the WOHIA was about Māori and whānau ora and that the right people in the Māori  community were consulted and given the opportunity to participate.

The same person noted that although in theory a WOHIA is about Māori, because the process was inclusive, the whole community will benefit from the outcomes.

The Council participant who, though overall was very positive about the WOHIA process, thought the WOHIA was a lot of work. It required time to carry out research, time to explain the process to Council Management and the time spent at meetings.

## 2.5	The report

The key informants were all positive about the report and noted it was well written, concise and gave a ‘good steer’ on how the draft Strategy should be rewritten and was a good record of the discussion.

However the WOHIA team leader had received one report of criticism of the report from one of the participants of the Appraisal Workshop. This person, who at the workshop was very critical of the draft Strategy and the way it had been developed, commented that the report did not reflect all the views presented at the meeting.

# 3	Outcome Evaluation

Section three reports on evaluation objectives three, four and five.

## 3.1	The short-term outcome – the impact of the HIA

The WOHIA report was sent as a submission on the draft Strategy to the Joint Hearings Committee of the three Local Territorial Authorities (the committee) dealing with the Strategy on behalf of the three Councils. The WOHIA team leader presented the submission and report at an oral hearing of submissions on the draft Strategy.  The report was well received at the hearing. In a letter to the WOHIA team leader, the Committee noted that it had directed the CAAG to make changes to the draft Strategy in line with the some of the recommendations included in the WOHIA Report.

The changes listed in the letter from the Committee included the following suggested changes:

- Ensure the Strategy is an ‘over-arching’ document – the removal of regulatory functions already occurring under legislation and in Council policies into a policy document

- Establish baseline statistics of existing problems and include data in the Strategy

- Update local facts and statistics ensuring they are relevant to Wairarapa

- Include a list of all relevant stakeholders/organisations

- Include the Actions Table from the HIA submitted by the Wairarapa DHB

- Change of the Goal to the Vision.

Though this letter did not explicitly state that all of the recommendations of the WOHIA be adopted, in the minutes and report from this meeting which the WOHIA team leader received at a later date, it is clear that all of the recommendations from the WOHIA have been included in the Committee’s suggested changes to CAAG.

The WOHIA made five overall recommendations, each with a subset of tasks. The recommendations are:

| 1. | Further develop the draft Strategy |
| --- | --- |
| 1.1 | Develop a clear and comprehensive problem description of alcohol harm within the Wairarapa to set the context for the draft Strategy. |
| 1.2 | Better describe the existing actions in the draft Strategy and which organisation/s will have responsibility for them. |
| 1.3 | Develop a joint vision that engages the three Councils and stakeholders. |
| 1.4 | Re-engage stakeholders to understand existing activity, what resources require reallocation and what new actions are required to achieve the joint vision. |
| 2. | Clearly identify roles and responsibilities within the draft Strategy and the holistic implementation plan |
| 2.1 | Provide leadership within the draft Strategy by assigning responsibility for each action to an existing regional governance group of senior decision makers. |
| 2.2 | Put three columns in the action section of draft Strategy - outline the lead organisation, those organisations who will support each action and be jointly responsible, and outline whether the action is: - Currently provided with existing resources (which includes labours cost, non-labour costs, time and money) - Existing with increased resources - Existing with decreased resources - New resources needed and what these might be See proposed template in Appendix B. (of the WOHIA Report) |
| 2.3 | Identify a key person in each organisation to coordinate the actions specified above. |
| 2.4 | Once the above actions are set up, develop a Memorandum of Understanding (MOU) between stakeholders and community groups around the draft Strategy to ensure everyone is clear with regards to respective actions. |
| 3. | Develop, facilitate and own an implementation plan that is adopted and released at the same time as the draft Strategy |
| 3.1 | All three Councils to identify a person from their Council to become an active participating member of CAAG. |
| 3.2 | Review CAAG to ensure a comprehensive membership and have input into the holistic implementation plan, for example media (and their role in the cause and solutions). |
| 3.3 | Set up focus groups with community members to get buy-in to the draft Strategy and to make the implementation plan community-centric. |
| 4. | Develop a communication strategy as a component of the implementation plan |
| 4.1 | Use CAAG to identify key populations so education messages can be targeted at specific groups within the community. |
| 4.2 | Ensure clear consistent education messages are delivered to the community using simple, everyday language. Ensure that any messages used are proven to be effective at reducing alcohol-related harm for the target population group and aligns with national key messages from ALAC. Note that messages such as “it’s OK not to drink” should also be considered as a legitimate component of any message campaign. |
| 4.3 | Develop partnerships with the media (newspapers) to promote the implementation of the draft Strategy’s key messages and safe responsible drinking. |
| 5. | Develop a Monitoring and Evaluation framework for the draft Strategy |
| 5.1 | Identify how each action is to be evaluated, by whom, and the timeframe by which the action is to be evaluated within. |
| 5.2 | Put the above evaluation points in columns in the action sections of the draft Strategy to ensure clarity around the evaluation measures. See proposed template in Appendix B. (of the WOHIA Report) |
| 5.3 | Identify what local monitoring data is available. Investigate modest changes to collection and reporting of such data to further understand the issue of alcohol-related harm in the local context. |

Another positive outcome of the WOHIA is that the WOHIA team leader from the DHB has been seconded onto the CAAG writing group to assist with the rewriting of the Strategy.

- 3.2	 WOHIA buy-in

All the key informants believed the WOHIA got good buy–in from DHB and the Councils. Early meetings were held in December when the WOHIA was first proposed and before the WOHIA process itself began to explain how HIA worked . The Council participant thought the early meetings were useful as they made the process and the expectations clear.

The DHB staff noted the WOHIA had senior management signoff and approval and that a number of senior managers from the DHB were involved in the process. The Māori Health Directorate supported the WOHIA right from the very beginning of the project. They were an important part of the consultation process and valuable advisors.

Two of the participants familiar with the HIA process said that though they felt the Council staff were sceptical in the beginning, the staff ‘came around’ very quickly and it was easy to engage with them. Both felt it would be easy to ‘sell’ HIA to the Councils again, especially if it was highlighted how useful the process would be in the development of Long Term Council Community Plans (LTCCP).

These two participants recommended going to the combined Council meeting (South Wairarapa, Masterton and Carterton Councils) to give a presentation on HIA – how it works, how Councils might be able to use HIA for other issues and how it can be used as a consultation process. The interviewees noted in ‘selling’ HIA it is important to make it very clear how Councils would benefit from the process and how it could create ‘wins’ for both the Council and the community.  These two participants agreed they would like to see HIA used in other projects and in other areas because it is a structured way of consulting with the community, a good way of getting people involved and a very effective method of looking at the impacts of policies and strategies.

All participants spoken to said they would participate in another HIA and described it as a valuable way of examining why a policy/strategy is being developed, clarifying who the initiative is intended to target and what the impacts of it might be. Participants also noted that it is a good way of enhancing relationships and developing collaboration. Two of the participants did however note that there were already good collaborative effects going on in the Wairarapa and described it as a ‘very cohesive community’ with ‘very good networks working in mental health, violence and safer communities work’.

The Council participant also believed Council Management would be willing to participate in another HIA but was wary of the time and resource needed to arrange the necessary consultation.

# 4	Discussion and Conclusions

Overall the feedback and evaluation for the WOHIA was positive. While it did not meet all of its aims those involved believed it was a positive process and participants identified a wide range of strengths in the process.

- 4.1	The short term impact of the WOHIA

There have been two positive short term outcomes of the WOHIA.  One was acceptance of all of the recommendations of the WOHIA by the Joint Hearing Committee of the three Local Territorial Authorities (TLA). This committee directed CAAG to rewrite the draft Strategy, which was one of the recommendations of the WOHIA, and to include all of the other recommendations of the WOHIA.

The second positive outcome is that the WOHIA team leader has been seconded onto the CAAG writing group to redraft the Strategy.

One of the key informant participants who had been part of the CAAG team which wrote the draft Strategy said the WOHIA had helped to ‘pull the Strategy back to having key targets’ and give it ‘more focus’. This person noted the draft Strategy had got ‘airy-fairy and waffly’ and was happy with the recommendations that came from the WOHIA.

Clearly the WOHIA has added value to the planning process of the Wairarapa Alcohol Strategy.

- 4.2	Did the WOHIA meet its objectives?

While not all of the objectives of the WOHIA were met, it seems the failure to meet these aims may have been more to do with the ambitious aims rather than a failure of the WOHIA process.

There was insufficient evidence to make the link between alcohol strategies, partnerships and consistency of approach with alcohol related harm and health outcomes. However in reaching this conclusion the WOHIA was able to make recommendations to ensure a redeveloped Strategy would be cognisant of exploring these links.

Local data which identified alcohol related inequalities, particularly for Māori and youth in the Wairarapa, were not available. However, by including a recommendation that a clear and comprehensive problem description of alcohol harm within the Wairarapa be developed in order to set the context for the draft Strategy the WOHIA was successful in highlighting the need for good local baseline data to be established. This was included in the recommendations put forward by the Committee to CAAG to be included in the redrafting of the Strategy.

The aims which related to identifying the current strengths in the community and providing guidelines and recommendations to key stakeholder groups on how to support, implement and develop the draft Strategy were considered to have been achieved. The recommendation in the WOHIA that specific organisations and their roles and responsibilities be included in the revised Strategy was agreed to by the Committee and included as one of the directives to CAAG in the re-writing of the Strategy. In addition, the WOHIA team believes the commitment and collaborative effort of the large number of organisations that participated in the WOHIA is likely to strengthen the co-operation when the Strategy is implemented later.

When asked if the WOHIA had met its objectives one of the key informants commented on the difficulty of dealing with alcohol related harm at the local level without national level strategies to support the work and noted the need for local and national strategies to be aligned.

- 4.3	The strengths and constraints of the WOHIA process

All of the key informant interviewees, and an overwhelming majority of the comments on the evaluation forms from the both Screening/Scoping and Appraisal Workshops, were positive about the strengths of the WOHIA process. The clarity of the process, the structured way of consulting with the community, the opportunity for discussion and relationship building were all mentioned as strengths of the WOHIA process.

The limited time frame for the WOHIA was the primary constraint noted by all the key informants. However several noted that one benefit of the short timeframe was that it helped to maintain focus and momentum.

One of the difficulties mentioned by several people was that some of the people who attended the WOHIA meetings did not understand the process and that this had the potential to ‘derail’ progress. Good facilitation of the meetings, which was another of the strengths identified, ensured that the groups were able to move forward and that the meetings were able to make a valuable contribution to the development of the final WOHIA recommendations.

- 4.4	Other evaluation objectives and positive outcomes

- The key informants all felt that good buy-in had been achieved. There was senior management level support for the WOHIA at the DHB and, though to a lesser extent, also at the Councils.

- Early work by the Health Promoter who met with and talked with more than 20 stakeholder groups before the WOHIA began ensured support from a wide range of organisations. The Council participant mentioned that this early support and explanation of the WOHIA process allowed her to explain the process fully to Senior Council staff and that it had been an important part of getting buy-in.

- Clearly the WOHIA was able to assist the Councils involved to develop a stronger Strategy based on evidence and effective community collaboration. Further work on developing a partnership between the Councils and the DHB could facilitate future effective HIA processes.

- It may be worth following up on the recommendation of two key informants who suggested presentations be made to the Combined Council Meeting of the three Territorial Local Authorities (Masterton, Carterton and South Wairarapa) involved in the Wairarapa Alcohol Strategy to further promote the use of HIA in the development of policy and particularly for their LTCCPs.

- In any future WOHIA or HIA explaining the process and the issues under consideration very clearly at the beginning of the Screening, Scoping and Appraisal workshops is necessary to make sure discussion is effective, focused and productive.

- 4.5	Conclusions

- The Learning by Doing Fund provided the Wairapapa DHB with funding for this WOHIA. The evaluation suggests the draft Wairarapa Alcohol Strategy, the Councils who are signatory to it and the local organisations who work to deal with alcohol related harm in the community have benefitted significantly from the WOHIA process.

- In response to the WOHIA recommendations and other submissions on the draft Strategy it is to be revised.

- The Wairarapa DHB’s Public Health team have increased their knowledge, skills and confidence in managing and implementing HIA. The mentoring provided by the WOHIA consultant was acknowledged as having been helpful in this process.

- The positive response of the organisations involved in the WOHIA could be used to further promote WOHIA and HIA in policy and strategy development in the Wairarapa.

# Appendix 1: Schedule for key informant interviews

## Questions for direct participants

The evaluation objectives

The evaluation of the WOHIA has the following objectives:

1.   To provide information to assist in improving the HIA process for future HIA work.

2.   To determine, in terms of process:

- if the objectives of the WOHIA were met

- the strengths of the WOHIA process

- the constraints of the WOHIA process

- possible ways the WOHIA process could have been improved

- whether the resources used throughout the WOHIA process were used  effectively.

3. To determine, in terms of impact:

- the impact of the WOHIA on the Wairarapa Alcohol Strategy

- if the WOHIA added value to the planning process? If so in what ways?

- if the recommendations were / weren’t taken on board, why / why not, and the consequences .

4. With regard to overall issues the evaluation aims to identify:

- key factors that achieved buy-in into the WOHIA process and outcomes, particularly at the senior management and political level

- key lessons from this WOHIA.

5. With regard to short-term outcome evaluation:

- will the WOHIA encourage ongoing monitoring of health impacts by those whose policies or programmes are the subject of the WOHIA

- whether or not the recommendations were accepted by the three Councils.

Do you have any questions before we start?

- What was your involvement with the HIA process? How and why did you become involved?

- Based on your experience, what do you think were the main strengths of the HIA process?

- Was there anything that you think constrained the HIA process?

- Have you any suggestions of how the HIA process might have been improved?

- What resources were used in the HIA process? Do you think these were used effectively? If not, why not?. What might have been done to use them more effectively ?

- In your view did the HIA achieve its objectives? Did it? If yes – in what way? If not, why not?

6(a) assess the links between alcohol strategies, partnership working and consistency of approach, with regard to alcohol related harm and health outcomes in the Wairarapa?

6(b) identify existing alcohol related inequalities in Wairarapa health and wellbeing outcomes, in particular, for Māori and youth

6(c) identity the potential positive and negative impacts of the draft Strategy on health and wellbeing

6(d) identify current strengths within the community to undertake the draft Strategy, as well as gaps, limitations and resource development needs that will ensure the draft Strategy is sustainable

6(e) provide evidence-based recommendations to enhance the draft Strategy’s potential positive impacts on health and wellbeing and mitigate potential negative impacts

6(f) provide some guidelines and recommendations to key stakeholder groups on how to support, implement and develop the draft Strategy within their organisations and in partnership with other agencies and organisations.

- What attempts were made to gain [senior management] buy in  to the HIA ? Was buy-in achieved?

  - senior management at the DHB?  If yes, in what way. If not, why not?

  - senior management at the 3 councils? If yes, in what way. If not, why not?

  - with any of the other participants ? CAAG? If yes, in what way. If not, why not?

- Do you think the consultation process (screening/appraisal) achieved successful engagement with stakeholders? Gathered useful information from the participants? If not why not? If yes, why?

- Do you think working with the other stakeholders on this HIA will help with collaboration on future policies/projects? Why? How?

- Do you think the HIA process has helped put health on the agenda for stakeholders for whom it is not their primary focus? Why? How?

- Do you think the HIA has added value to the strategy development process to date. If so, in what way?

- Were the recommendations of the HIA adopted by the three councils? Why/why not?

Are there any other comments you would like to make?

- Questions for community stakeholders

The evaluation objectives

The evaluation of the WOHIA has the following objectives:

1.   To provide information to assist in improving the HIA process for future HIA work.

2.   To determine, in terms of process:

- if the objectives of the WOHIA were met

- the strengths of the WOHIA process

- the constraints of the WOHIA process

- possible ways the WOHIA process could have been improved

- whether the resources used throughout the WOHIA process were used  effectively.

3. To determine, in terms of impact:

- the impact of the WOHIA on the Wairarapa Alcohol Strategy

- if the WOHIA added value to the planning process? If so in what ways?

- if the recommendations were / weren’t taken on board, why / why not, and the consequences .

4. With regard to overall issues the evaluation aims to identify:

- key factors that achieved buy-in into the WOHIA process and outcomes, particularly at the senior management and political level

- key lessons from this WOHIA.

5. With regard to short-term outcome evaluation:

- will the WOHIA encourage ongoing monitoring of health impacts by those whose policies or programmes are the subject of the WOHIA

- whether or not the recommendations were accepted by the three Councils.

Do you have any questions before we start?

- What was your involvement with the HIA process? How and why did you become involved?

- Based on your experience, what do you think were the main strengths of the HIA process?

- Was there anything that you think constrained the HIA process?

- Overall how did you find the process? Was it positive, how? Negative, how?

- Have you any suggestions of how the HIA process might have been improved?

- Would you be prepared to take part in another HIA given your experience with this one? If no, why not? If yes, why?

- Do you think the consultation process (screening/appraisal) worked well and reached the right people in the community? If not why not? If yes, why?

- Have you seen a draft or the final HIA report and/or the recommendations that went into the submission of the draft strategy? If yes, what did you think of it/them?

- Have the councils adopted the recommendations? (Or, do you think the councils are likely to adopt the recommendations?) If not, why not?

- Do you think working with the other stakeholders on this HIA will help with collaboration on future policies/projects? Why? How?

- Do you think the HIA process added value to the strategy development process? If so, in what way?

Are there any other comments you would like to make?

# Appendix 2: Evaluation forms given to participants

## Screening/Scoping workshop

By completing this brief questionnaire you will help the Whānau Ora HIA Team to keep on improving its processes for collecting stakeholder/community input into its HIAs.  No names or other identifying information are required on this form.

|  | Statement | Strongly agree | Agree | Disagree | Strongly disagree |
| --- | --- | --- | --- | --- | --- |
| 1. | I understand why Whānau Ora HIA is undertaken |  |  |  |  |
| 2. | I understand why we are doing Whānau Ora HIA on this topic |  |  |  |  |
| 3. | I understand what the main focus of this Whānau Ora HIA will be |  |  |  |  |
| 4. | I felt I was able to contribute to the decisions about what this Whānau Ora HIA was going to focus on |  |  |  |  |
| 5. | I want to continue to be involved in future parts of this Whānau Ora HIA |  |  |  |  |
| 6. | I will consider the Whānau Ora HIA process for other projects that are/ will be occurring |  |  |  |  |

7.	The main strengths of the session were?

8.	What could have been done to improve the scoping session?

9.	 Any other comments?

Thank you very much for providing this feedback

## Appraisal workshop

By completing this brief questionnaire you will help the Whānau Ora HIA Team to keep on improving its processes for collecting stakeholder/community input into its HIAs.  No names or other identifying information are required on this form.

|  | Statement | Strongly agree | Agree | Disagree | Strongly disagree |
| --- | --- | --- | --- | --- | --- |
| 1. | I understand why Whānau Ora has the potential to be affected by a draft Alcohol Strategy |  |  |  |  |
| 2. | Overall, this workshop has been useful for identifying potential intended and unintended effect of the draft Alcohol Strategy |  |  |  |  |
| 3. | The participants have suggested ways this draft plan might affect the determinants of wellbeing for families |  |  |  |  |
| 4. | This workshop has been a good opportunity for me to develop or maintain links with people across the sector/s |  |  |  |  |
| 5. | The workshop has been a good opportunity to contribute my views and ideas for the enhancement of the draft Alcohol Strategy |  |  |  |  |
| 6. | I will consider the HIA process for other projects that are/ will be occurring |  |  |  |  |

7.	The main strengths of this appraisal workshop were?

8.	What could have been done to improve the appraisal workshop?

9.	 Any other comments?

Thank you very much for providing this feedback

The WOHIA team digitally recorded the meeting so that the evaluator could listen to recordings from the meetings and workshop.

See Appendix 1

See Appendix 2

A full list of the attendees in included in the Appendices of the WOHIA Report

See Appendix 2

The schedules are included in Appendix 1